## Table 1
Product Backlog
Name | Description | Estimated Effort | Priority | State
Learn API | Learn how to use API to extract date | 5 hours | 0 | ☑️
Create SQL database | Create local SQLite database to hold all games in collection | 7 hours | 1 | ☑️
create menue screen | create main screen and navigationg bar | 2hours | 2 | ☑️
create manage collection screen | create manage collection page including adding and removing functionality | 2 hours | 2 | ☑️
create recommentation screen | add daily recommendation user interface | 2 hours | 2 | ☑️
create parser | create parser for game list and game infomation | 9 hours | 5 | ☑️
connect UI to database | connect user interface to local database | 4hours | 6 | ☑️
remove games from collection | connect user interface to local database, remove games from personla collection | 3 hours | 7 | ☑️
search game by name | user can search game from collection by name | 3hours | 8 | ☑️
search game by number of players | user can search games from collection by number of players | 3hours | 8 | ☑️
search game by year | user can search games from collection by year | 3 hours | 8 | ☑️
search game by playTime | user can search games from collection by play time | 3 hours | 8 | ☑️
add game to collection | search game, add games using api from website and importing to local database | 6hours | 12 | ☑️
fix problems of screens | make navigation bar seeable all the time | 4 hours | 13 | ☑️
import games from website | import game collection from website if user has an account in BGG | 7hours | 14 | ☑️
daily recommendation | remcommend games to users on a daily basis | 5hours | 15 | ☑️
beautify pages | add some image view to the app | 3hours | 16 | ☑️
integrate buttons | add some navegation buttons including cancel, go back | 4hours | 17 | ☑️
show details of game | people can see the details of game when click a game item | 8 hours | 18 | ☑️
documentation | finish documentation and diagrams | 4 hours | 19 | ☑️