## Table 1
Sprint Backlog
user story | Task Not Started | Task In Progress | Task Complete | 10/23 | 10/24 | 10/25 | 10/26 | 10/27 | 10/28 | 10/29 | 10/30 | 10/31 | 11/1 | 11/2 | 11/3 | 11/4 | 11/5 | 11/6 | 11/7 | 11/8
As a user, i can open the app and switch screens |  |  | Learn API | 10/23: 2; 10/27: 4
|  |  | Create SQL database | 10/23: 3; 10/24: 2; 10/25: 0
create menue screen | bar: 10/24
create manage collection screen | bar: 10/24
As a user, i can manage my collection including add games and remove games from collection. |  |  | add game to collection | 10/26: 3; 10/27: 2
|  |  | create parser | 10/27: 6; 10/28: 2
|  |  | connect UI to database | 10/27: 3
remove games from collection | bar: 10/27; 10/30
As a user, i can search games from collection by filters. |  |  | search game by name | 10/27: 3
|  |  | search game by number of players | 10/27: 3
|  |  | search game by playTime | 11/6: 3; 11/7: 2
|  |  | search game by year | 11/6: 3; 11/7: 2
As a user, i can acquire some game reccomendations |  |  | create recommentation screen | 10/27: 2
|  |  | daily recommendation | 10/27: 4; 11/1: 4; 11/4: 6
As a user, i can import games from website |  |  | import games from website | 10/30: 4; 11/1: 5; 11/3: 0
As a user, i can see the details of game |  |  | show details of game | 11/8: 4
As a user, i can have a delightful experience . |  |  | integrate buttons | bar: 10/30; 11/1
fix problems of screens | bar: 11/3
beautify pages | bar: 10/27; 10/30; 11/3